## Overview
Project Name
Overview
Reference Information | Location | Comments
Use Cases & Requirements | [Link]
Change Log | Person | Date | Test Instructions
Created Doc | Jenney Chang | 2018-12-14
| Jeremey DeHay | 2018-12-14
Test Results Summary (Auto Calculated) | Number | Percent
Total Test Cases Passed | 28 | 93.33%
Total Test Cases Failed | 2 | 6.667%
Total Test Cases Remaining | 0 | 0%

## LoginCreate Account
Test Info |  | Test Summary |  |  | Instructions
Test Scenario | Login and Account Creation | Total Passed | 7 |  | In the "Status" column, use Pass, Fail, or Not Started.
Test Environment | Sandbox instance | Total Failed | 0 |  | Totals and color highlighting will update automatically based on the Status column
|  | Total Remaining | 0
Test Case ID | Test Case Description | Expected Result | Test Data | Actual Result | Status | Tester | Date | Comments
A-0001 | UI: Create Account button | Stage Change |  | switch Create Account stage | Pass | JC | 2018-12-14
A-0002 | Create Account: with no data | Throw Error |  | invalid text entry alert | Pass | JC | 2018-12-14
A-0003 | Create Account: invalid email | Throw Error | bobby@me | invalid email or password alert | Pass | JC | 2018-12-14
A-0004 | Create Account: invalid password | Throw Error | jc | invalid email or password alert | Pass | JC | 2018-12-14
A-0005 | Create Account: using existing account info | Throw Error | bobby@bobby.com, jc123041 | email address unavailable | Pass | JC | 2018-12-14
A-0006 | Successful Create Account w/ Create Account Button | Stage Change | willy12@willy.com, jc123041 | stage change: Sign In | Pass | JC | 2018-12-14
A-0007 | Sign In with created Account | Stage Change | willy12@willy.com, jc123041 | stage change: main app | Pass | JC | 2018-12-14

## Main App
Test Info |  | Test Summary |  |  | Instructions |  |  | © Eric R. Dayal
Test Scenario | Menus & Add, Edit, Delete functionality | Total Passed | 10 |  | In the "Status" column, use Pass, Fail, or Not Started.
Test Environment | Sandbox instance | Total Failed | 1 |  | Totals and color highlighting will update automatically based on the Status column
Test Data Source | [link] | Total Remaining | 0
Test Case ID | Test Case Description | Expected Result | Test Data | Actual Result | Status | Tester | Date/Time | Comments
MA-0001 | UI Menu Bar functionality | Popup stages |  | Popup stages | Pass | JC | 2018-12-14
MA-0002 | UI Button Bar functionality | Popup stages |  | Popup stages | Pass | JC | 2018-12-14
MA-0003 | Add Account: error with empty Account Name tf | Throw error |  | Throw error | Pass | JC | 2018-12-14
MA-0004 | Add Account: add generated password w/default setting | Populate password field | 7_:+hpD,6t | Successful | Pass | JC | 2018-12-14
MA-0005 | Password Gen: custom pw w/ check box | Populate listview |  | Invalid Selection | Fail | JC | 2018-12-14 | generator only accepts select all option
MA-0006 | Password Gen: select all check box options | Populate listview |  | Successful | Pass | JC | 2018-12-14
MA-0007 | Password Gen: varying password length | Populate listview | 1930-10-20 | Successful | Pass | JC | 2018-12-14
MA-0008 | Edit: errow with empty account name field | Throw error |  | Successful | Pass | JC | 2018-12-14
MA-0009 | Edit: load generated password w/ default settings | Populate password field | 8pw¦So.kMh | Successful | Pass | JC | 2018-12-14
MA-0010 | Edit Account function | Tableview Refresh | Joseph | Successful | Pass | JC | 2018-12-14
MA-0011 | Delete Account function | Tableview Refresh | Joseph | Successful | Pass | JC | 2018-12-14
MA-0012 | Save Button functionality | save account details to file
MA-0013 | Open Button functionality | open encrypted file

## User Interface
Test Info |  | Test Summary |  |  | Instructions |  |  | © Eric R. Dayal
Test Scenario | UI elements and functionality | Total Passed | 11 |  | In the "Status" column, use Pass, Fail, or Not Started.
Test Environment | Sandbox instance | Total Failed | 1 |  | Totals and color highlighting will update automatically based on the Status column
Test Data Source | [link] | Total Remaining | 0
Test Case ID | Test Case Description | Expected Result | Test Data | Actual Result | Status | Tester | Date/Time | Comments
UI-0001 | Create Account: Buttons & Textfields | stage change |  | Successful | Pass | JC | 2018-12-12
UI-0002 | Sign In: Buttons & Textfields | stage change |  | Successful | Pass | Eric D. | 2018-12-12
UI-0003 | Main: Menu Bar | popup |  | Successful | Pass | JC | 2018-12-12
UI-0004 | Main: Button Bar & Images | Window popups |  | Successful | Pass | JC | 2018-12-12
UI-0005 | Main: Table View | Populates & Refreshes |  | Successful | Pass | JC | 2018-12-12
UI-0006 | Password Gen: Checkboxes | Change listview result |  | Partial Success | Fail | JC | 2018-12-12 | only select all works
UI-0007 | Password Gen: Buttons & text field | stage change |  | Successful | Pass | JC | 2018-12-12
UI-0008 | Password Gen: ListView | Populates | generated data | Successful | Pass | JC | 2018-12-12
CO-0009 | Add Account: Textfields & Buttons | stage change |  | Successful | Pass | JC | 2018-12-12
CO-0010 | Edit Account: Textfields & Buttons | stage change |  | Successful | Pass | JC | 2018-12-12
CO-0011 | Delete Account: textfield & buttons | stage change |  | Successful | Pass | JC | 2018-12-12
CO-0012 | Settings: Buttons, textfield, combo box | stage change |  | Successful | Pass | JC | 2018-12-12